## Sheet1
DasCODE UE Research and Design Deliverables Planning
Deliverables | Dependencies | Date of Completion
Journey Maps
Admin |  | End of February
Engineer |  | March 10th
Template Writer | User Stories Interview names | First week of April
Manager | User Stories Interview names | First week of April
Consolidated | Completion of all other interviews and other journey maps | 3rd week of April
User Interviews
Admin |  | Completed
Engineer |  | End of February
Template Writer | User stories Interview names Script | End of March
Manager | User stories Interview names Script | End of March
Prioritize User Stories
Personas | To be discussed with team. What type of information do they want to see from persona? Completion of Interviews | TBD
Report and Presentation | Completion of interviews and journey maps | 3rd week of April
Designs
Initial UI Cleanup |  | End of February
CLI
Web UI
Admin Screens |  | None required
Engineer Screens | Main task/workflows of user based on interviews | swag 2 weeks. End of March
Template Writer Screens | Main task/workflows of user based on interviews | swag 2 weeks
Manager Screens | Main task/workflows of user based on interviews | swag 2 weeks